## Product Backlog
Commercial Bank of Ethiopia CORE System LEASE MANAGEMENT SYSTEM (phase 1)
ID | User Story | Product Description | Estimated Date | Product Goal/Business Value | Priority (P1,P2,P3,P4, P5) | Acceptance Criteria | Remark
US-01 | Perform calculations for lease liability, assess the value of the right-of-use asset, calculate depreciation expenses, and establish finance discharge | For lease liability calculation, contract start date, contract end date, advance payment, lease incentive discount rate, and installment date must be provided or input by the user. |  | lease leablity calculation, right of use asset calculations, finance discharche calculations | P1 | the system should calculate the lease leiablity, right of use asset and finance discharche | 18 September (4 weeks)
US-02 | after the calculations the system should generate report monthly, yearly and quarterly | The system will compile all the calculations that have been performed and generate reports according to the specific criteria provided by the business team. These reports can be exported in various formats, including Excel or any other format as required by the team. |  | generate report monthly yearly an quarterly | P2 | the system should return the report monthly, quarterly and yearly | 18 October (4 weeks)

## Iteration Plan 01
Commercial Bank of Ethiopia CORE System LEASE MANAGEMENT SYSTEM: Iteration 01
|  |  | Business Owner: |  | The Team (backend) |  | Team Sync Time/Daily Standup
[5 empty] | Elias Yeshanew |  | 8:30 - 8:45 Daily
|  |  | Sprint/Iteration Duration |  | Frontend |  | Team Sync Mode
|  |  | 18-Sep-23 -To- 17-Oct-23 |  | Gadisa Teklu |  | Face to Face
[5 empty] | Tester |  | Estimation Unit
[5 empty] | Jalela Mengistu |  | 1Unit = 7.5hrs
User Stories | Description | Sprint/ Iteration ID | Sprint/Iteration Backlog | Sprint/Iteration Description | Tasks to be acomplished | Developer | Start Date | End Date | Estimation in Unit | Dependancy | Definition of Done | Remark | Status
Perform calculations for lease liability, assess the value of the right-of-use asset, calculate depreciation expenses, and establish finance discharge | For lease liability calculation, contract start date, contract end date, advance payment, lease incentive discount rate, and installment date must be provided or input by the user. | TB01 | 1. Provide a thoroughly tested calculation for lease liability, right-of-use asset valuation, depreciation expenses, and financial discharge expenses. 2. Enable the business team to input their queries and obtain the desired outputs effortlessly. |  | Include fields for contract start date, contract end date, advance payment, total contract price, discount rate, and the first installment date of the lease within the "add contract" section. | Frontend | 2023-09-18 | 2023-09-22 | 5 |  | Deliver page to display informations with contract registration and view contarct lists |  | Completed
[5 empty] | Incorporate buttons for "Contract List View" and "New Contract" onto the dashboard page. | Frontend | 2023-09-23 |  | 1 |  |  |  | Completed
[5 empty] | Develop Database Design | Backend | 2023-09-25 | 2023-09-29 | 5 |  | Deliver page to mange lease's |  | Completed
[5 empty] | Develop User Interface Design and test | Frontend | 2023-10-02 | 2023-10-10 | 7 |  |  |  | Completed
[5 empty] | leasea information detail DB design and communicating with front end. | Backend | 2023-10-11 | 2023-10-12 | 2 |  | Deliver Database Design for lease information and discussing with all the team |  | Completed
[5 empty] | contract registration DB Design and communicating with front end. | Backend | 2023-10-12 | 2023-10-17 | 6 |  |  |  | Completed
[5 empty] | political region DB Design and communicating with front end. | Backend | 2023-10-12 | 2023-10-13 | 2 |  |  |  | Completed
[5 empty] | company region DB Design and communicating with front end. | Backend | 2023-10-13 | 2023-10-14 | 2 |  |  |  | Completed
[5 empty] | district DB Design and communicating with front end. | Backend | 2023-10-14 | 2023-10-15 | 2 |  |  |  | Completed
[5 empty] | Branch DB Design and communicating with front end. | Backend | 2023-10-15 | 2023-10-16 | 2 |  |  |  | Completed
DB = Database

## Iteration Plan 02...
Commercial Bank of Ethiopia CORE System LEASE MANAGEMENT SYSTEM: Iteration 02
|  |  | Business Owner: |  | The Team (backend) |  | Team Sync Time/Daily Standup
[5 empty] | Elias Yeshanew |  | 8:30 - 8:45 Daily
|  |  | Sprint/Iteration Duration |  | Frontend |  | Team Sync Mode
|  |  | 18-Oct-23 -To- 18-Nov-23 |  | Gadisa Teklu |  | Face to Face
[5 empty] | Tester |  | Estimation Unit
[5 empty] | Jalela Mengistu |  | 1Unit = 7.5hrs
User Stories | Description | Sprint/ Iteration ID | Sprint/Iteration Backlog | Sprint/Iteration Description | Tasks to be acomplished | Developer | Start Date | End Date | Estimation in Unit | Dependancy | Definition of Done | Remark | Status
Following the calculations, the system is expected to produce reports on a monthly, yearly, and quarterly basis. | The system will compile all the calculations that have been performed and generate reports according to the specific criteria provided by the business team. These reports can be exported in various formats, including Excel or any other format as required by the team. | TB02 | 1. Provide pages for managing individual contracts. 2. Create pages for viewing contract lists and details. 3. Develop pages for generating reports. |  | Design a report generation module and Implement logic to compile calculations into report data. | All team members | 2023-10-18 | 2023-11-30 | 5 |  | 1.users must manage their detail information 2. the admin must able to assign the users based on their specialization and department. | Inprogress | 99%
[5 empty] | Develop functionality to manage lease information through Create, Read, Update, and Delete (CRUD) operations, and ensure thorough testing of this functionality. | All team members | 2023-10-26 | 2023-12-01 | 7 |  |  | inprogress | 99%
[5 empty] | Implement the ability to manage report information using Create, Read, Update, and Delete (CRUD) operations and perform comprehensive testing to validate this functionality. | All team members | 2023-11-06 | 2023-12-01 | 7 |  |  | inprogress | 99%
[5 empty] | Optimize database queries and performance for efficient report generation and Design a user interface for accessing and downloading generated reports. | All team members | 2023-11-16 | 2023-12-01 | 3 |  |  | inprogress | 75%
*CRUD = Create, Read, Write & Delete,