## Sheet1
Commercial Bank of Ethiopia core system work report
|  |  | Business Owner: |  | The Team (backend) |  | Team Sync Time/Daily Standup
[5 empty] | Elias Yeshanew |  | 8:30 - 8:45 Daily
|  |  | Sprint/Iteration Duration |  | Frontend |  | Team Sync Mode
|  |  | 18-Sep-23 -To- 17-Oct-23 |  | Gadisa Teklu |  | Face to Face
[5 empty] | Tester |  | Estimation Unit
[5 empty] | Jalela Mengistu |  | 1Unit = 7.5hrs
NAME | Description | Sprint/ Iteration ID | Sprint/Iteration Backlog | Sprint/Iteration Description | Tasks to be acomplished | Developer | Start Date | End Date | Estimation in Unit | Dependancy | Definition of Done | Status
The Team (backend) | For lease liability calculation, contract start date, contract end date, advance payment, lease incentive discount rate, and installment date must be provided or input by the user. | TB01 | 1. Provide a thoroughly tested calculation for lease liability, right-of-use asset valuation, depreciation expenses, and financial discharge expenses. 2. Enable the business team to input their queries and obtain the desired outputs effortlessly. |  | Include fields for contract start date, contract end date, advance payment, total contract price, discount rate, and the first installment date of the lease within the "add contract" section. | Frontend | 2023-09-18 | 2023-09-22 | 5 |  | Deliver page to display informations with contract registration and view contarct lists | Completed
Elias Yeshanew |  |  |  |  | Incorporate buttons for "Contract List View" and "New Contract" onto the dashboard page. | Frontend | 2023-09-23 |  | 1 |  |  | Completed
[5 empty] | Develop Database Design | Backend | 2023-09-25 | 2023-09-29 | 5 |  | Deliver page to mange lease's | Completed
Frontend |  |  |  |  | Develop User Interface Design and test | Frontend | 2023-10-02 | 2023-10-10 | 7 |  |  | Completed
Gadisa Teklu |  |  |  |  | leasea information detail DB design and communicating with front end. | Backend | 2023-10-11 | 2023-10-12 | 2 |  | Deliver Database Design for lease information and discussing with all the team | Completed
[5 empty] | contract registration DB Design and communicating with front end. | Backend | 2023-10-12 | 2023-10-17 | 6 |  |  | Completed
Tester |  |  |  |  | political region DB Design and communicating with front end. | Backend | 2023-10-12 | 2023-10-13 | 2 |  |  | Completed
Jalela Mengistu |  |  |  |  | company region DB Design and communicating with front end. | Backend | 2023-10-13 | 2023-10-14 | 2 |  |  | Completed
[5 empty] | district DB Design and communicating with front end. | Backend | 2023-10-14 | 2023-10-15 | 2 |  |  | Completed
[5 empty] | Branch DB Design and communicating with front end. | Backend | 2023-10-15 | 2023-10-16 | 2 |  |  | Completed
[5 empty] | Monitoring Responding Summarizing |  | 2023-09-06 | … |  |  | corrupted message on LAU swift | Ongoing
Ambachew Tarekegn
[5 empty] | Logging Monitoring Responding Summarizing |  | 18/0ct |  |  |  | PAN MASKING ISSUE 1 | Ongoing
…
[5 empty] | Logging Monitoring Responding Scompleted |  | 2023-10-06 | 09/0ct |  |  | summarizing T24 request signOnNamename include the SAML issuer ID | completed
[5 empty] | monitoring Responding Summarizing |  | 2023-08-11 | 2023-09-14 |  |  | Wrong Entries passed during FT post | completed
Eyobed Israel |  |  |  |  | logging Monitoring Responding Summarizing |  | 2023-10-04 | 13/0ct |  |  | customer order a single mobile transaction but the system post twice | completed
[5 empty] | Monitoring Responding Summarizing |  | 2023-09-16 | 2023-10-18 |  |  | unauthorized TXN | completed
[5 empty] | Logging Monitoring Responding Summarizing |  | 18/0ct | … |  |  | FT.COMMISSION.TYPE | Ongoing
[5 empty] | Monitoring Responding Summarizing |  | 2023-09-12 |  |  |  | Internal Server Error on ARCIB | Ongoing
Getinet Sileshi |  |  |  |  | Develop a subroutine seamlessly integrated into a no-file Enquiry system and transform it into a consumable Temenos web service. |  | 2023-07-27 | 2023-08-10 |  |  | This enhancement enables the display of customer accounts, including pertinent details such as Debit Interest and Credit Interest. | completed
[5 empty] | Create a program capable of accepting PAN number digits and encoding them into the corresponding alphabets. |  | 2023-07-28 | 2023-07-29 |  |  | This program masks required digits of PAN number. | completed
[5 empty] | Implement Temenos web services at the following endpoints: [http://10.1.15.195:8080/CustAdtnlInfo/services?wsdl] [http://10.1.15.195:8080/RestrictionService/services?wsdl] |  | 2023-08-12 | 2023-10-02 |  |  | This are some of Temenos Web Service Projects Implemented at different times as requisted | completed
[5 empty] | Actively engage in the implementation of the SWIFT message Integrity (SWIFTLAU) in alignment with our follow-up on the ticket submitted to the Temenos Customer Support team. |  | 2023-08-18 |  |  |  | This project demonstrates our commitment to ensuring the integrity and security of SWIFT messages within our system | Ongoing
Kasahun Abebe Borko and Jalela Mengistu |  |  |  |  | Credit operation training |  | 2023-10-18 |  |  |  |  | Ongoing
Abraham Mamo ,Natnael Tefera ,Tesfanesh Yisaiase |  |  |  |  | onjob training | [6 empty] | waiting for project presentation
project work
Selamawit Demissie,Eleni Abrham and Tibarek Teshome |  |  |  |  | Collect all unauthorized FT ,TT transaction and comminicate respective organs to clear it before upgrade. |  | Weekly |  |  |  | Unauthorized Transactions | Ongoing
|  |  | Eleni Abrham |  | Reporting material loss |  | Weekly |  |  |  | Material loss will be compiled and send | Ongoing
[5 empty] | T24 Application Security Audit Findings |  | Weekly |  |  |  | segregation of duties and breaking down of processes between the 3rd level and 1st level support. | Ongoing